## Projektplanlægger
Gantt chart for Hi-fi Corner
Fremhæv et tidsrum til højre. Derpå følger en forklaring af diagrammet. |  |  |  |  | Fremhævning af tidsrum: | 1 |  |  | Varighed for plan | [5 empty] | Faktisk startdato |  |  |  |  | % fuldført |  |  |  |  | Faktisk (ud over plan) | [7 empty] | % fuldført (ud over plan)
AKTIVITET | STARTDATO FOR PLAN | VARIGHED FOR PLAN | FAKTISK STARTDATO | FAKTISK VARIGHED | PROCENTDEL FULDFØRT | TIDSRUM
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create a repository on gitHub for the project | 1 | 1 | 0 | 0 | 0%
Analyse the project in a Word document | 2 | 2 | 0 | 0 | 0%
Analyse the design in previous mentioned document | 4 | 2 | 0 | 0 | 0%
Make a Gantt chart | 6 | 2 | 0 | 0 | 0%
Create a project in your repository and add all these issues | 8 | 2 | 0 | 0
Design the JSON data structure | 10 | 2 | 0 | 0 | 0%
Create the necessary files for the website | 12 | 1 | 0 | 0 | 0%
Get/find/create and edit image material | 13 | 10 | 0 | 0 | 0%
Code the main HTML structure - Header, Nav, Footer + Necessary CSS | 23 | 3 | 0 | 0 | 0%
Code the "Home" page HTML + CSS + JS | 26 | 4 | 0 | 0 | 0%
Code the "Brands" page HTML + CSS | 30 | 2 | 0 | 0 | 0%
Code the "Shop" front page HTML + CSS | 32 | 2 | 0 | 0 | 0%
Write the JSON file which contains data on all the products | 34 | 10 | 0 | 0 | 0%
Code the "Shop" main page HTML + CSS + JS | 44 | 10 | 0 | 0 | 0%
Code the "Shop" individual product page HTML + CSS + JS | 54 | 5 | 0 | 0 | 0%
Code the product search function | 59 | 5 | 0 | 0 | 0%
(Code the extra challange) | 0 | 0 | 0 | 0 | 0%